## Weekly_summer
Summer 2018, weekly calendar & deliverables
| 2018-05-07 |  | 2018-05-14 |  | 2018-05-21 |  | 2018-05-28 |  | 2018-06-04 |  | 2018-06-11 |  | 2018-06-18 |  | 2018-06-25 |  | 2018-07-02 |  | 2018-07-09 |  | 2018-07-16 |  | 2018-07-23 |  | 2018-07-30 | 2018-08-06 | 2018-08-13 | 2018-08-20 |  | 2018-08-27 | 2018-09-03
Meetings
UVa collab | 9th - Cara |  |  | 18th-Alissa/Barbara | [25 empty] | Classes on 28th
Int/Ext Boards |  | 11th-lunch |  |  |  | 24th-skype
other/travel |  |  |  |  | 21st-Lisa/pilot |  |  | 30th - D.O. |  |  |  |  | 17/18-NY, Libby, etc. | [14 empty] | all data, all the time |  | DAAD doc.
Deliverables (MS prep)
for trip students | kazu, n/a | [10 empty] | student groups & supplies (15th) |  |  |  | contact list (1) | apps, exercises (5th) |  |  |  | maps to print |  |  |  | all last minute comms. |  |  | box.net collations
for summer Ras | wk 1 sch |  | wk2 sch / archive samples |  | replit/set-ups /paper.js |  | extra api examples |  |  |  | field tools/tasks prepped |  | design / dev prompts and frameworks | [5 empty] | all guide formats, exercise outlines
| wk 1 code samples |  | wk 2 code samples |  | 80% time teaching |  | 80% time teaching
for internal decisions/teams | this - schedule coord |  | ui ideas for proto |  |  |  | rev exer/ui |  | decision on fall (late)
exercises/matrix to ML
for internal/external collab |  | agenda |  | agenda |  | agenda |  |  |  |  | nyc sch | agenda
|  | summer/fall steps |  |  |  | summer/fall steps
for specific grants | dates tally |  | set-up documentation | [19 empty] | oct kress - get estimates in august
| biblo call |  | code/design/activity/pdf & web | [19 empty] | write-ups (clearly won't have time)
Labor / Time commitment / input
BM |  |  |  |  | nyc ideas/outreach |  |  |  | work-up schedule |  |  |  | nyc trip | [5 empty] | rev. samples/exerc. | [5 empty] | review - prep to lead
ML |  |  | pilot/UI follow-up 1 |  |  |  | pilot/UI follow-up 2 |  |  |  | contacts/groups | ML-16th | [6 empty] | rev. samples/exerc. | [5 empty] | review - prep to lead |  |  |  | UI - review fall vs. grant work
MS | lessons & deliv. sum/fall |  | lessons & deliv. sum/fall |  | teaching & agendas |  | teaching & D.O. day |  | teaching (50%) |  | field fun (50%) |  | field & code (50%) |  | field & code (50%) |  | field & code (50%) |  | field & code (50%) |  | field & code (50%) |  | field & code (50%) |  | last minute everything |  |  | all data transfer - notes |  | biblio & grant instructions
| paper.js ssample |  | api samples (zotero org.) | [5 empty] | raster coll (3), osm (2), teach, nyc & german prep (5) |  |  |  | (nyc) dessau (2), siteshp (3), teach & german (4) |  |  |  | map layouts & print prep (3), collate (2), other (3) |  |  |  | logistics (3), guides (2), teach (5) |  |  |  | fyi - crazy course prep |  |  | fuck - iit classes, 20th |  | fuck - uva classes, 28th | tbd - uva/chicago juggling
wrap and review
[5 empty] | front-end & prototype intensive - 3 wks | [5 empty] | field intensive |  | field/code prototyping
MI |  |  |  |  | 50% code - exercises / q |  | 75% code |  | 100% code |  | 40% field testing, 60% des |  |  | api pgs/anno |  | api/natural language |  | api other (60%) |  | field & vis int (100%) |  | 2d, 3d int (100%) |  | 2d, 3d int (100%) | 2 days collation |  |  |  |  | to grant, to dev team -
YC |  |  |  |  | 100% code |  | 100% code |  | 100% code |  | 40% field testing, 60% des |  |  | api pgs/anno |  | field rev. |  | field rev/sample (60%) |  | field & vis int (100%) |  | 2d, 3d int (100%) |  | 2d, 3d int (100%) | 2 days collation
KJS |  |  |  |  | 100% code |  | 100% code |  | 100% code |  | 40% field testing - out WTF |  | out MTW - 'quick starts' |  |  | field rev. |  | field rev/sample (60%) |  | metadata guides (60%) |  | field guides (100%) |  | processing/syn (100%) | 2 days collation |  |  |  | notes/revision of fieldwork - for nyc strategies
[10 empty] | shuffle w/ attendance |  | or 20/40-field doc, design
CG/Scholars |  |  | GC - check-in |  | re-cap/video meetings? | [6 empty] | check-in |  |  |  |  | GC - topo due | [11 empty] | fall - follow-up on GIS workshops, video
WM/Iath |  |  | WM - check-in | [8 empty] | check-in | [16 empty] | fall - follow-up on data, tagging tasks
RA existing |  |  | task status for all | [28 empty] | on-boarding (again)
(finish in overtime) |  |  |  |  | tag protocols Zotero |  | Heather's biblio |  | field fun prep |  |  |  | all the missing materials, all RA prompts/feedback and code reviews | [5 empty] | outstanding germany issues, build and rebuild classes (fall), outside design/dev. likely | [8 empty] | teaching, always teaching, design/dev.
see 3 week break down

## Daily_4 weeks
|  | 2018-05-21 |  |  | (meeting 12-1pm) | KJS out | 2018-05-28 |  | Dumbarton Oaks |  |  | 2018-06-04 |  | team fieldwork - basics/sampling for secondary feedback - exercise use/refinement |  |  | 2018-06-11 |  | KJS out for wedding - W to F |  |  |  | 2018-06-18 |  | KJS out for wedding - M to T/W
prep | 8 | M | T | W | Th | F | M (memorial day) | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F |  | M | T | W | Th | F
[22 empty] | BM/LG(?)/MS in NYC |  | workshopping
4hr morning | 10 | orientation (1) | enviro/tools (1) | node/sublime ex. set-up | trans modu (1.5) | brainstorm and free-build |  | orient (.5) | field day | async & scope (1) | review/share | node - local use (1) | check-in: ideas - mvp | photo & drawing | video & audio | kite/balloon | triangulations (4) | measures & matter (4) | 3 day design - wrap together | check-in: ideas - mvp | check-in: ideas - mvp |  |  |  | schedule splits by focus
| 11 | syntax,cond(1.5) | iteration/loops/objects - (1.5) |  | node/npm/webpack (1) | review / share |  | traversals/listen (1.5) | (half or full day) | 3 paper ex (1) | data in rel db (1-tutorials) | 3 data cleaning (1) | api data build (4) | lightrm, archives, data | mounts, edits | " | gps, laser, how-to | " | ideation-design-research | build | build |  | warp day | existing ux ideas
| 12 | split | split | p5.js lib unpack | (meeting out) | idea-elements (1) |  | dom ux with paper (4) | half day extension | ajax calls / axios (1) | api rest queries (30) | zotero/dpla/paper (1) | " | " | " | " | " | " | build | " | " |  | collate, format | research tools
| 1 | repl.it 6 ex (1.5) | repl.it 6 ex (1.5) | tools/mdn | p5-img as data (1) | interact build (3) |  |  |  | promises (1) | sql lite queries (3) | idea-elements (1) | " | " | " | " | " | processing | " | " | " |  |  | design revisions
lunch | 2 | (meeting out)
| 3 | fnct/scope/arrays(1.5) | oop, classes (1.5) | p5, interactions | " | team build |  | team build |  | api calls & promise ex(2) | return to/finish tutorials | api data build (3) | " | " | " | recap tutorial | " | design discussion | " | " | "
3hr afternoon | 4 | split | split | review / share | data edits build (3) | " |  | " |  |  | " | " | review/share | processing | processing | processing | processing | ops/timing/feedback | " | " | review/share
| 5 | repl.it 6 ex (1.5) | repl.it 3 ex (1.5) | git / document | team build | review/share/git |  | review/share |  |  | review/share | " | git/document | processing/taggin | processing/taggin | design discussion | processing/taggin | " | " | " | git/document
|  | overflow | overflow | overflow | overflow | overflow |  | overflow |  | overflow | overflow | overflow | overflow | overflow | overflow | overflow | overflow | overflow | overflow | overflow | overflow |  | overflow | overflow
7
| 8 | pilot/UI follow-up 2 prep | [5 empty] | pilot/UI follow-up 2 revisions |  |  |  | data cleaning, manipulations
| 9 | exercise materials, prompt structures for field | [5 empty] | exercise materials, prompt structures for field
| 11 | freelance/week revisions prep | [5 empty] | freelance/week revisions prep |  |  |  | freelance/week revisions prep |  |  |  |  | groups/supplies list revised/prepped
12
dom-operations
in advance of start |  |  |  | p5/paper | p5/paper images | prototyping - design thinking
CLI set-up and use |  | 15 min chunks | 15-30 min chunks | 1 hr install build | 3hr build - explore | 3hr build - explore |  | 3hr build - explore |  | 20 - 1 hr chunks | 20 - 2 hr chunks | 20 min - 7 hr build data vis/data use |  | 1 hour setup : 4 hours collab fieldwork : 2 hours processing |  |  |  |  | 21 hr build data vis/data use
github account and use |  |  |  |  | read-in data | user data - imported data |  | user data-dom raw |  | outside data | outside data struct | outside data mixed |  | testing tools, scale/timing of efforts, processing, ops for creative mis-use |  |  |  |  | outside data mixed and visualized
prep all |  | run through tutorials |  | tools/researching | options, git tutorial, prototype tutorials |  |  | css, traversal tutorial |  | async / promises | db / rest-ful api tutorial | local node / nonweb work |  | re-presentation capture/play |  |  |  |  | composite design - field grab also
equivalent to 13 class sessions |  | write/adpt exercises | write/adpt exercises | node to paper setup | design task in paper | design task in paper |  | design task in paper working through multiple data sources / types edits |  |  |  | design task in paper / api / local data |  | emphasis on what can quick & dirty do, show, find…. & what does synthesis look like |  |  |  |  | design task in paper / api / local data / zotero / dpla and free building
[5 empty] | early lunch | canvas - operations |  | div canvas elements |  |  | database exercises
html and canvas components
|  |  |  | node/babel/modules | [5 empty] | biodiversity heritage
|  |  |  | write afternoon activities | [5 empty] | dpla - search and display
write p5 exercise solution/prompt - Thursday and Friday work
pull together selection on prototyping
atomized data to structured data and interactions
defining parameters - landscape, materials, composites to enable meaningful aggregations